## Slide 1: Incentivised Milestones – Programme Timeline
Target vs. current forecast finish — Period 05
Complete
Forecast on target
Behind target
+5d
later than target date
-5d
ahead of target date
1
EIS H - Entry into Service
Target & P05: 26 May 2026
Complete
2
EIS N W4 Finish 28d Blockade
Target & P05: 27 Jun 2026
Complete
3
Gledholt 16-day Blockade Complete
Target & P05: 05 Oct 2026
Forecast On Target
4
RBA/2 Baker Viaduct Complete
Target & P05: 21 Jan 2027
Forecast On Target
5
EIS K - Entry into Service – Huddersfield Station
Target & P05: 01 Feb 2027
Forecast On Target
6
EIS J – Entry into Service - Deighton Station
Target & P05: 01 Feb 2027
Forecast On Target
7
EIS N4 - W3A: Area 2 and 3 Civils Works Complete for fast lines
Target: 21 Feb 2027
P05 Finish: 29 Jan 2027 (-23d)
Forecast On Target
8
EIS L7 - Thornhill Bridge Complete and Ready for EIS L Blockade
Target & P05: 28 Mar 2027
Forecast On Target
Commentary — Period 05
4 · RBA/2 Baker Viaduct Complete — 5-day movement recovered in period; forecast finish pulled back from 26 Jan 2027 (P04) to the 21 Jan 2027 incentivised target, clearing the Behind Target status reported last period.
No entries were recorded in the tracker's Variance Comments column this period; the note above is derived from the Period Movement and finish-date columns.
Milestones ordered chronologically by incentivised target date; spacing is not to scale. Source: Incentivised Milestones tracker (Period 05).